## Sheet1
COSC1076 ¦ Semester 1 2021
Assignment 2 ¦ Weekly Update Tracking Sheet
Group Name:
Group Member: | Ethan Rayner |  | Progress Classes: | Ahead
Group Member: | B |  |  | On-track
Group Member: | C |  |  | Behind
Group Member: | D |  |  | Way Behind
Tutor: | Dale
Class: | APT
|  | Week 7 | Goals | Tutor Notes | Indidvidual Updates | Ethan Rayner | B | C | D
|  |  | Group Formed |  | Weekly Contribution
|  |  | MS Team created |  | Issues
|  |  | Git Repo created |  | Other Notes
|  | Progress | Way Behind
|  | Week 8 | Goals | Tutor Notes | Indidvidual Updates | Ethan Rayner | B | C | D
|  |  | Choice of where to use linked list, vector & array |  | Weekly Contribution
|  |  | Initial Design of ADTs (classes and potential methods) |  | Issues
|  |  | Main menu |  | Other Notes
User Prompt (for gameplay), but no/minimal error checking
Linked List implementation
Implementation(s) or suitable ADTs wrapper for the use of vector and arrays, game logic not required
ADT implementation for storing information, game loop logic not required
|  | Progress | Way Behind
|  | Week 9 | Goals | Tutor Notes | Indidvidual Updates | Ethan Rayner | B | C | D
|  |  | Load/Save to/from data strucutres (doesn't require integration with main menu or game loop) |  | Weekly Contribution | Node class, linked list deconstructor, tile class, constructor and getters. Helped Joanna with board function.
|  |  | Initialisation of data strctures for new game |  | Issues | None
|  |  | Write Tests Cases for common uses |  | Other Notes
Gameplay for single round
|  | Progress | Behind
|  | Week 10 | Goals | Tutor Notes | Indidvidual Updates | Ethan Rayner | B | C | C
|  |  | Fully complete implementation and error free |  | Weekly Contribution | Game class, player class (place and replace outline), moved print board to game class, added player hands and added player scores to board layout, began working on tracking turn order.
|  |  | Full error checking of user prompt |  | Issues
Other Notes
Final Tests
Group Report Written
|  | Progress | Way Behind